## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Gather project requirements, hospital stakeholder needs, and define project scope | MUST HAVE | Project Brief | Ujjwal,Aarya,Priya | 3- Completed
S1 | S1 | US-002 | Collect and document data dictionary for Pharmacy, Lab, and Patient Operations | MUST HAVE | Raw Datasets | Aaryan,Deepika,Vidhya | 3- Completed
S2 | S2 | US-003 | Clean datasets, handle null values, remove outliers, and standardize date formats | MUST HAVE | Data Dictionary | Shankar,Ananya,Vasudha | 3- Completed
S2 | S2 | US-004 | Integrate multi-department data and build KPI calculation logic engine | MUST HAVE | Cleaned Datasets | Yogyatha,Suja,Bhuvana | 3- Completed
S3 | S3 | US-005 | Conduct department-wise operational analytics for Pharmacy, Lab, OT, and Emergency | SHOULD HAVE | KPI Framework | Saksham,Eluri Tejaswini,Ukasha | 3- Completed
S4 | S4 | US-006 | Build interactive dashboard visuals, KPI cards, filters, and UI/UX layout | MUST HAVE | Analytics Data | Kartik Bawne,Supra | 3- Completed
Note on F1: ====== ID#AAABYLGvqXM Sumeet Kumar Barua08 (2024-11-14 13:03:52) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 80 | 3 | 7 | 8 | 4 | 6 | 5 | 9 | 4 | 6 | 4 | 9 | 5 | 5 | 5
US-001 | TASK-001 | Gather project requirements & scope | 2026-08-08 | 2026-08-09 | Ujjwal,Aarya,Priya | Requirements | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-002 | Document Pharmacy & Lab raw data schemas | 2026-08-09 | 2026-08-10 | Aaryan,Deepika,Vidhya | Data Understanding | Completed | 8 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-003 | Perform data cleaning, null handling & date standardization | 2026-08-10 | 2026-08-12 | Shankar,Ananya,Vasudha | Data Preprocessing | Completed | 12 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-004 | Build multi-department data integration pipeline & KPI formulas | 2026-08-12 | 2026-08-14 | Yogyatha,Suja,Bhuvana | Data Engineering | Completed | 12 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-005 | Execute department-wise operational analytics (OT, Emergency, Lab) | 2026-08-14 | 2026-08-16 | Saksham,Eluri Tejaswini | Analytics | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
US-006 | TASK-006 | Design UI/UX layout, KPI cards, and dynamic slicers | 2026-08-16 | 2026-08-18 | Ukasha,Supra | Dashboard Dev | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 0
US-007 | TASK-007 | Final Dashboard integration, defect fixes, unit testing & PPT deck | 2026-08-18 | 2026-08-20 | Kartik Bawne | Integration & Lead | Completed | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5
Note on D2: ====== ID#AAABYLGvqXg Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABYLGvqXI Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABYLGvqXQ Sumeet Kumar Barua08 (2024-11-14 13:03:52) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABYLHdiCk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABYLGvqX4 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABYLGvqXU Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABYLGvqXs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABYLHdiCs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABYLGvqXY Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABYLGvqXo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABYLGvqXw Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABYLGvqX8 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABYLGvqXE Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABYLGvqXc Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABYLHdiCo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABYLGvqX0 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABYLGvqXk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2024-08-08 | 2024-08-11 | Ujjwal,Aarya,Priya | Defining standard data dictionary upfront | Working on isolated raw data files | Daily team sync meetings | Created unified project schema
2 | S2 | 2024-08-11 | 2024-08-14 | Aaryan,Deepika,Vidhya | Automated script validation for null values | Manual data cleaning in spreadsheets | Modular code structure | Implemented Pandas cleaning scripts
3 | S3 | 2024-08-14 | 2024-08-17 | Saksham,Eluri Tejaswini,Suja | Cross-checking KPI formulas with raw data | Delaying bug updates on Defect Tracker | In-depth department analysis | Validated revenue & patient SLA KPIs
4 | S4 | 2024-08-17 | 2024-08-20 | Ukasha,Supra,Kartik Bawne | Continuous integration & UI testing | Hardcoding filter values in visuals | Parallel PPT deck updates | Automated deployment & clean UI layout

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | Inconsistent column names across Pharmacy and Lab raw CSVs | Standardized column naming convention across all team members
S2 | Day 5 | Negative duration values found in Ambulance response timestamps | Corrected datetime parsing logic in Python preprocessing script
S3 | Day 8 | Slicer filter lag when navigating across multi-department dashboard tabs | Optimized data model relationships and DAX query measures
S4 | Day 11 | Alignment misconfigurations when exporting final executive PDF report | Fixed page view dimensions and visual container grid padding
S4 | Day 13 | Final PPT coordination bottleneck across team members | Kartik Bawne assigned centralized deck consolidation responsibilities