## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Yogyatha | 2026-08-08 | Mismatch in total revenue KPI calculation logic | Sprint 2 | Yogyatha, Tejaswini | Calculation Error | Updated formula logic in script | 2026-08-09 | Closed | Verified with raw data
2 | Aaryan | 2026-08-10 | Date filter range not updating laboratory test charts dynamically | Sprint 4 | Aaryan,Supra | UI / Filter Issue | Re-indexed slicer relationships | 2026-08-11 | Closed | Slicers working fine
3 | Saksham | 2026-08-12 | Null values present in OT bed occupancy dataset post-cleaning | Sprint 2 | Saksham,Deepika | Data Quality | Imputed missing values with median | 2026-08-13 | Closed | Dataset re-validated
4 | Kartik Bawne | 2026-08-18 | Executive Overview KPI cards layout misaligned | Sprint 4 | Kartik Bawne | UI Layout | Adjusted responsiveness & layout | 2026-08-18 | Closed | Tested on layout
5 | Ukasha Zari Ansari | 2026-08-19 | Ambulance response time calculation showing negative duration values | Sprint 3 | Ukasha Zari Ansari | Logic Bug | Fixed timestamp subtraction order | 2026-08-19 | Closed | Durations now positive